Project Execution Process

OR

Work Breakdown Structure (WBS)

(Phase Wise)

| Project Type: | Ordering and booking system |
| --- | --- |
| Project Name: | Online food ordering and table booking |
| Document referred: | Functional document of the project |
| Document type: | WBS (Project execution process) |

Table showing Work break down in Phases

Phase I

| Module Description | Working Days |
| --- | --- |
| Front end - Database design - Home page design creation and approval. Admin - Admin Login/profile - Listing Admin user - Adding admin user - Editing Admin user - Deleting Admin user - Manage General Settings - PayPal personal account setting. - Social page URL’s. - Manage Email Template - List Email Templates - Edit Email Templates QA for Phase 1 modules | 05 days |

Phase II

| Module Description | Working Days |
| --- | --- |
| Front End - Home page integration a. Header Section. b. Middle Section. c. Footer Section. - User Registration a. Customer b. Restaurant owner - Login - Normal login - Login with Facebook - Forgot password functionality a. Send password on email address - Contact us page a. Send email to admin - CMS Page a. CMS Page linking b. CMS Displaying. - Customer Dashboard - Profile - Edit profile 8. Restaurant owner Dashboard - Profile - Edit profile Back End - User management - Contact us content management. - CMS management. - Manage template - Category management QA for Phase 2 modules | 8 days |

Phase III

| Module Description | Working Days |
| --- | --- |
| Front End - Create restaurant page a. Select template b. Upload logo c. Fill other details - Create menu - Search module a. Post code b. Delivery c. Food type d. Cuisine e. Food name - Restaurant menu page - Advertisement module - Add dish to cart - Confirm order by filling required details - Book table module Back End - Restaurant page template management - Orders management - Advertisement management - Table booking orders management - SMS template management QA for phase 3 modules | 12 days |

Phase IV

| Module Description | Working Days |
| --- | --- |
| Front End - Coupon module - Checkout module - Payment gateway integration a. DPS (Direct payment solutions) b. PayPal - Cancel order - SMS API integration Back End - Coupon management - Payment management QA for phase 4 modules | 05 days |

Please note, above time estimation is totally depend upon reference documents as mentioned above, if there is any change in functionality / in the assumption document, above time estimation will change accordingly.